| Delivery Plan – Combined (Date Order) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Who (Stream / Locale) | Days of Works | Construction Activity | Planned Start Date | Planned End Date | Resource Name | Site Address | TMP Plan Reference | CitiPower LIS Number | Resource Required | OH Hrs | UG Hrs | Day/ Night Works | Start / Finish Time | Parking Bays Required |
| Key: Service Stream = blue ¦ Locale = orange ¦ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OH CPL (Luke’s job) | 1 | OH (minor works) | 1/11 | 1/11 | CitiPower | Burnley St |  |  |  |  |  | Day | 0700-1700 |  |
| Locale | 3 | Civil works | 4/11 | 6/11 | Locale Civil | Appleton St | 1485091-04 |  |  |  |  | Day | 0700-1700 |  |
| Locale | 1 | Civil works | 9/11 | 9/11 | Locale Civil | Burnley St | 1485091-02 |  |  |  |  | Day | 0700-1700 |  |
| Locale | 1 | Jointing assist | 9/11 | 9/11 | Locale Civil | Appleton St | 1485091-04 |  |  |  |  | Day | 0700-1700 | Outside 2,4,6, 8, 8A,14, 14A Appleton St. |
| Locale | 1 | Jointing assist | 10/11 | 10/11 | Locale Civil | Burnley St | 1485091-02 |  |  |  |  | Day | 0700-1700 |  |
| Locale | 1 | Backfilling | 10/11 | 10/11 | Locale Civil | Appleton St | 1485091-04 |  |  |  |  | Day | 0700-1700 | Outside,14, 14A Appleton St. |
| Locale | 1 | Backfilling | 11/11 | 11/11 | Locale Civil | Burnley St | 1485091-02 |  |  |  |  | Day | 0700-1700 |  |
| Service Stream | 2 | Excavation | 12/11 | 13/11 | 4 Civil | Appleton St | 1485099-01 | 2808 |  |  |  | Day | 0700-1630 | Outside 24, 22, 18 Appleton St. |
| Service Stream | 5 | Excavation | 16/11 | 20/11 | 4 Civil | Appleton St | 1485099-01 | 2807, 2806 |  |  |  | Day | 0700-1630 | Outside 18, 16, 14, 14A Appleton St. |
| Service Stream | 4 | Excavation | 24/11 | 27/11 | 4 Civil | Appleton St | 1485099-01 | 2805 |  |  |  | Day | 0700-1630 | Outside 8, 8A, 10 Appleton St. |
| Service Stream | 1 | Excavation | 30/11 | 30/11 | 4 Civil | Appleton St | 1485099-01 |  |  |  |  | Day | 0700-1630 | Outside 2, 4, 6 Appleton St. |
| Service Stream | 1 | Cable haul | 1/12 | 1/12 | 4 Civil | Appleton St | 1485099-01 | 2805-2808 |  |  |  | Day | 0700-1630 | Outside 2,4,6, 24,22, 18 Appleton St. |
| OH CPL (Agha’s job) | 1 | OH | 2/12 | 2/12 | CitiPower | Appleton St | 1485099-01 | 2805-2808 |  |  |  | Day | 0700-1630 |  |
| Service Stream | 1 | Cable jointing | 2/12 | 2/12 | Service Stream | Appleton St | 1485099-01 | 2805-2808 |  |  |  | Day | 0700-1630 | Outside 2,4,6, 8, 8A, 18,16,14, 14A Appleton St. |
| Service Stream | 1 | Backfill | 3/12 | 3/12 | 4 Civil | Appleton St | 1485099-01 | 2805-2808 |  |  |  | Day | 0700-1630 | Outside 2,4,6, 8, 8A, 18,16,14, 14A Appleton St. |
| Total | 23 | working days (1/11 to 3/12) |  |  |  |  |  |  |  |  |  |  |  |  |