	Delivery Plan – Combined (Date Order)
	

	Who (Stream / Locale)
	Days of Works
	Construction Activity
	Planned Start Date
	Planned End Date
	Resource Name
	Site Address
	TMP Plan Reference
	CitiPower LIS Number
	Resource Required
	OH Hrs
	UG Hrs
	Day/ Night Works
	Start / Finish Time
	Parking Bays Required

	Key:  Service Stream = blue   |   Locale = orange   |   
	

	OH CPL (Luke’s job)
	1
	OH (minor works)
	1/11
	1/11
	CitiPower
	Burnley St
	
	
	
	
	
	Day
	0700-1700
	

	Locale
	3
	Civil works
	4/11
	6/11
	Locale Civil
	Appleton St
	1485091-04
	
	
	
	
	Day
	0700-1700
	

	Locale
	1
	Civil works
	9/11
	9/11
	Locale Civil
	Burnley St
	1485091-02
	
	
	
	
	Day
	0700-1700
	

	Locale
	1
	Jointing assist
	9/11
	9/11
	Locale Civil
	Appleton St
	1485091-04
	
	
	
	
	Day
	0700-1700
	Outside 2,4,6, 8, 8A,14, 14A Appleton St.

	Locale
	1
	Jointing assist
	10/11
	10/11
	Locale Civil
	Burnley St
	1485091-02
	
	
	
	
	Day
	0700-1700
	

	Locale
	1
	Backfilling
	10/11
	10/11
	Locale Civil
	Appleton St
	1485091-04
	
	
	
	
	Day
	0700-1700
	Outside,14, 14A Appleton St.

	Locale
	1
	Backfilling
	11/11
	11/11
	Locale Civil
	Burnley St
	1485091-02
	
	
	
	
	Day
	0700-1700
	

	Service Stream
	2
	Excavation
	12/11
	13/11
	4 Civil
	Appleton St
	1485099-01
	2808
	
	
	
	Day
	0700-1630
	Outside 24, 22, 18 Appleton St.

	Service Stream
	5
	Excavation
	16/11
	20/11
	4 Civil
	Appleton St
	1485099-01
	2807, 2806
	
	
	
	Day
	0700-1630
	Outside 18, 16, 14, 14A Appleton St.

	Service Stream
	4
	Excavation
	24/11
	27/11
	4 Civil
	Appleton St
	1485099-01
	2805
	
	
	
	Day
	0700-1630
	Outside 8, 8A, 10 Appleton St.

	Service Stream
	1
	Excavation
	30/11
	30/11
	4 Civil
	Appleton St
	1485099-01
	
	
	
	
	Day
	0700-1630
	Outside 2, 4, 6 Appleton St.

	Service Stream
	1
	Cable haul
	1/12
	1/12
	4 Civil
	Appleton St
	1485099-01
	2805-2808
	
	
	
	Day
	0700-1630
	Outside 2,4,6, 24,22, 18 Appleton St.

	OH CPL (Agha’s job)
	1
	OH
	2/12
	2/12
	CitiPower
	Appleton St
	1485099-01
	2805-2808
	
	
	
	Day
	0700-1630
	

	Service Stream
	1
	Cable jointing
	2/12
	2/12
	Service Stream
	Appleton St
	1485099-01
	2805-2808
	
	
	
	Day
	0700-1630
	Outside 2,4,6, 8, 8A, 18,16,14, 14A Appleton St.

	Service Stream
	1
	Backfill
	3/12
	3/12
	4 Civil
	Appleton St
	1485099-01
	2805-2808
	
	
	
	Day
	0700-1630
	Outside 2,4,6, 8, 8A, 18,16,14, 14A Appleton St.

	Total
	23
	working days (1/11 to 3/12)
	



